## TestCase
Product Name |  | https://tenbea.com/ | TC Start Date | 13/09/2022 |  |  | TC Execution Start Date | 15/09/2022 | TEST CASE SUMMARY
Module Name |  | Projects,Tasks | TC End Date | 15/09/2022 |  |  | TC Execution End Date | 15/09/2022 | PASS | 18
Epic |  |  | Test Case Developed By | Rafeed Talukder |  |  | Browser (tested) | No | FAIL | 6
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir vi |  |  | Performance (tested) | No | Not Executed | 0
|  |  | Test Executed By | Rafeed Talukder |  |  |  |  | Out of scope | 0
[9 empty] | TOTAL | 24
SL | Module |  | Features | Test Cases | Exepected Result | Actual Result | Test Data | Test Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
TC001 | User Management |  | Registration | UI design cheaking | Position of Logo,search bar, registration,login are as is the requirment. | working properly as expected. | Not Applicable | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Check all elements as per requirment | Full_Page_SS001 |  | Passed
TC002 |  |  |  | Cheaking that registration form contains username,email,phn number,password and confirm password | 1.User Name 2.Email 3.Phone Number 4.Password and confirm password are must be here with proper UI design | working properly as expected. | Not Applicable | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Check all input fields are remain | Full_Page_SS001 |  | Passed
TC003 |  |  |  | Varify that tab function is working properly (Proper navigation) | 1.After using tab on user name field should go on email field 2. using tab on email field should go on phone field . 3. using tab on phone field should go on password field 4.using tab on password field should go on confirm password field | working properly as expected. | Not Applicable | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.In all input field used tab button so that the field was changed | Full_Page_SS001 |  | Passed
TC004 |  |  |  | Enter button is working aswell for create account | After pressing tab go to another field | working properly as expected. | Not Applicable | 1.Go to url with browser. 2.Click on register button->redirect to register page. |  |  | Passed
TC005 |  |  |  | All fields must have a valid placeholder & icon | 1.User Name should have username placeholder and icon 2.Email should have email placeholder and icon 3.Phone Number should have phone number and icon 4.Password and confirm password chould have password and confirm password placeholder with icon | working properly as expected. | Not Applicable | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Check all input fields placeholder | Full_Page_SS001 |  | Passed
TC006 |  |  |  | Varify that all mandatory field are marked with * sign | 1.Phone number & 2.Email & 3.Password & Confrom pasword must marked with * sign | Not working properly as expected. | Not Applicable | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Check all mandary input fields have * sign | Full_Page_SS001 |  | Failed
TC007 |  |  |  | A message or red allert will given when submit button is clicked without filling mandatory field | 1.Should alert on phone number,email & password field | All fields are required to filed , Not working properly as expected. | Not Applicable | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Without fillup any filed click on create account button | Required_Error_SS002 |  | Failed
TC008 |  |  |  | Input all valid information for create account | 1. At first loging it redirect to varification page & user must get a OTP number for varified account. | working properly as expected. | rafeed 01710864340 rafeedkhan591@gmail.com @123rafeed @123rafeed | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Input vald username,email,phone number,pass & confirm password as per mentioned on test data section 4.Press on submit button | OTP_SS003 |  | Passed
TC009 |  |  |  | After creating account with varification code then it should redirect to home page | 1.Should redirect to home page | Don’t go home page, stay on this page | Not Applicable | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Input vald username,email,phone number,pass & confirm password as per mentioned on test data section 4.Press on submit button and redirect to varification page 5.Input varification code then press enter. | After_OTP_SS004 |  | Failed
TC010 |  |  |  | Try to create user without entering any value | 1.Field is required error message must be shown at required fields | working properly as expected. | Not Applicable | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Without filling username,email,phone number,pass & confirm password 4.Press on submit button | All_field_required_SS005 |  | Passed
TC011 |  |  |  | Use Invalid User Name | 1.Please, Input valid username,which starts with althabet message must be shown | working properly as expected. | 123456 | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Input invald username as per mentioned on test data section. 4.Press on submit button | In_user_SS006 |  | Passed
[7 empty] | !@#$% |  | In_user_SS007
TC012 |  |  |  | Use Invalid phone number | 1.Phone number must be valid message shown | working properly as expected. | addhhscd @#$%^&*( | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Input invald phone number as per mentioned on test data section. 4.Press on submit button | Ph_Nm_SS009 |  | Passed
TC013 |  |  |  | Use Invalid email address | 1. Email address must be valid | Working properly as expected. | !@#$%^&@gamil.com asdfgh@gmail dhudcgmail.com | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Input invald email as per mentioned on test data section. 4.Press on submit button | email_SS010 |  | Passed
[6 empty] | Working not as expected | rafeed@gmail.c |  | Email_SS011 |  | Failed
TC014 |  |  |  | Use less than 6 character as password & confirm password | 1.Password should contain 6-12 character message must be shown | Don’t show any error message | 12345 123abc | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Input password and confirm as per mentioned on test data section. 4.Press on submit button | Pass_SS012 |  | Failed
TC015 |  |  |  | Use same value on password & confirm password field | 1.Should take as a password | working properly as expected. | 123abcd | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Input password and confirm as per mentioned on test data section. 4.Press on submit button | Pass_SS013 |  | Passed
TC016 |  |  |  | Use different value on password & confirm password field | 1.Error message must be shown | working properly as expected. | Password : 1234abcd Confirm password: abcd123 | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Input password and confirm as per mentioned on test data section. 4.Press on submit button | Pass_SS014 |  | Passed
TC017 |  |  |  | Try to register with existing account | 1.Should not consider as a account 2.Error message must be shown | working properly as expected. | User:rafeed email:rafeedkhan591@gmail.com phone:01710864340 pass:123abcd con pass:123abcd | 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Input all as per mentioned on test data section. 4.Press on submit button | Pass_SS014 |  | Passed
TC018 |  |  | Sign in | Check UI design | 1.Every thing should have as per requirment including heading & text field alignment | Heading alignment not as per expected | Not applicable | 1.Go to url with browser. 2.Click on login button->redirect to login page. 3.Check all elements as per requirment. | Signup_Header _SS015 |  | Failed
TC019 |  |  |  | Try to sign in without filling any value | 1.Should not login and red alert message must be shown | working properly as expected. | Not applicable | 1.Go to url with browser. 2.Click on login button->redirect to login page. 3.Without fillup any filed click on Login button | Signup_SS016 |  | Passed
TC020 |  |  |  | Try to sign in with invalid information | 1.Should not login and red alert message must be shown | working properly as expected. | username:qwerty password:1234567 | 1.Go to url with browser. 2.Click on login button->redirect to login page. 3.Fillup all filed with given data and click on Login button | Signup_Header _SS015 |  | Passed
[5 empty] | 1.User name is mendarory message must be shown | working properly as expected. | username: password:1234567 |  | Signup_Header _SS015 |  | Passed
[5 empty] | 1.Password is mendarory message must be shown | working properly as expected. | username:advdd password: |  | Signup_Header _SS015 |  | Passed
TC021 |  |  |  | Try to Sign in with valid information | 1.Should login & redirect to home page | working properly as expected. | username:rafeed password:123abcd | 1.Go to url with browser. 2.Click on login button->redirect to login page. 3.Fillup all filed with given value click on Login button | After_OTP_SS004 |  | Passed

## Report
Test Case Report
Project Name - | Tenbea.com
Module Name - | User management |  |  |  |  | Total No. | Status | Result :
Test Case Version - | 1 |  |  |  |  | 18 | PASS
Written By | Md.Rafeed Talukder |  |  |  |  | 6 | FAIL
Executed By | Md.Rafeed Talukder |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment :
Reviewed By | Sabbir vai |  |  |  |  | 0 | Out of Scope |  |  | Test Environment | Google Chrome Browser
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 18 | 6 | 0 | 0 | 24
Grand Total | 18 | 6 | 0 | 0 | 24
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Metrics
Test Metrics
Project Name- |  | Tenbea.com
Module Name- |  | User Management
Written By- |  | Rafeed
Executed By- |  | Rafeed
Reviewed By- |  | Sabbir vai
Total No. of Test Cases for all requirments | Total No. of Test Cases are weritten | No. of Requirments (As per client) | Avg No. Test Cases Per Requirments | No. of Test Cases Executed | No. of Test Cases Passd | No. of Test Cases Failed | No. of Test Cases Un-Executed | No. of Test Cases Blocked (Out of Scope) | No of Defecs Idenified (Failed) | Cricital Defects Found | Medium Defects Found | Low Defects Found | Customer Defects | No. of defects found in UAT | No. of defects Rejected | % of Test cases Executed | % of Test cases Not Executed | % of Test cases are Passed | % of Test cases are Failed | % of Test cases are Blocked
21 | 21 | 12 | 1.75 | 21 | 18 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 2 | 2 | 1 | 100 | 0 | 85.7143 | 28.5714 | 0
| Defect Density | Defect Removal Efficiency | Defect Leackage | Defect Reection Ratio | [6 empty] | All Calculation formula
| 0.5 | 75 | 0.33333 | 16.6667
1. No. of requirments = Submitted by client
2. Avg No. Test Cases Per Requirments = Total No. of Test Cases for all requirments / No. of Requirments(As per client)
3. % of Test Cases Executed = No. of Test Cases Executed / Total No. of Test Cases are weritten
4. % of Test Cases Not Executed = (No. of Test Cases Not Executed / No. of Test Cases are weritten) * 100
5. % of Test Cases Passed = (No. of Test Cases Passed / No. of Test Cases are Executed) * 100
6. % of Test Cases Failed = (No. of Test Cases Failed / No. of Test Cases are Executed) * 100
7. % of Test Cases Blocked = (No. of Test Cases Blocked / No. of Test Cases are Executed) * 100
8. Defect Density = No of Defecs Idenitify (Failed) / No. of Requirments(As per client)
9. Defect Leackage = (No. of defects found in UAT / No of Defecs Idenitify (Failed) ) * 100
10. Defect Rejection Ratio = (No. of defects Rejected / Number of Defects Raised as like No. of Test Cases Failed )* 100
10. Defect Removal Efficiency (DRE) = A / ( A+B ) * 100
A= No of Defecs Idenified (Failed)
B= No. of defects found in UAT or by customer

## Bug Report1
Bug Report
Project Name - | Tenbea.com
Module Name - | User Management
Written By - | Rafeed
Executed By - | Rafeed
Reviewed By- | Sabbir vi
S.N : BR001 Test Case ID: TC006 Defect Description: Mandatory filed varification with * sign Steps to Reproduce: 1.Go to url with browser. 2.Click on register button->redirect to register page. 3.Check all mandary input fields have * sign 4.Without fillup any filed click on create account button Environment: QA Module: User Management Severity: P3 ScreenShots: Responsible QA: Rafeed
S.N : BR002 Test Case ID: TC009 Defect Description: Unable to redurect to home page after login Steps to Reproduce: 1.Go to web site. 2. Create account Environment: QA Module: User Management Severity: P1 ScreenShots: Responsible QA: Rafeed
S.N : BR003 Test Case ID: TC014 Defect Description: Password verification with boundery value Steps to Reproduce: 1.Go to web site. 2.Enter less than boundery and more than boundery value Environment: QA Module: User Management Severity: P2 ScreenShots: Responsible QA: Rafeed
S.N : BR004 Test Case ID : TC018 Defect Description : UI header text align Steps to Reproduce: 1.Go to web site. 2.Enter Sign In button Environment : QA Module : Sign In Severity : P2 ScreenShots : Responsible QA : Rafeed
Required_SS001
SS001
SS 002
UI SS003